## Sheet1
System Name | Bubble Space
Members: | Rae Addison Duque
Al Jubail-Benz Engalla
Jeannie Margarett Verar
Statuses |  | Todo
In-Progress
Done
On-hold
[5 empty] | September |  |  |  | October
Tasks | Assignee | Date Started | Date Finished | Status | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
1. Functional Requirements | Rae Addison Duque | 2024-08-21 | 2024-09-23 | Done
2. Gantt Chart | Jeannie Margarett Verar | 2024-08-21 | 2024-09-23 | Done
3. ERD | Al Jubail-Benz Engalla | 2024-09-23 |  | Done
4. UI/UX Design
4.1. User Management | Rae Addison Duque | 2024-10-09 | 2024-10-12 | Done
4.2. Team Management | Rae Addison Duque | 2024-10-09 | 2024-10-12 | Done
4.3. Messaging/Interaction | Jeannie Margarett Verar | 2024-10-09 | 2024-10-12 | Done
4.4. Project Management | Al Jubail-Benz Engalla | 2024-10-09 | 2024-10-12 | Done
4.5. Task Management | Al Jubail-Benz Engalla | 2024-10-09 | 2024-10-12 | Done
4.6. Note Creation | Jeannie Margarett Verar | 2024-10-09 | 2024-10-12 | Done